## PAI
Project Action Items
PAI # | Date Created | Created By | Organizations Involved | PAI Description | Assigned To | Date Needed | Completion Date | Other Committees Involved | Action Taken | Current Status
001 | 2014-12-15 | Vpalamountain | High school | Secure space | Jdown | 2014-12-30 | 2014-12-18
002 | 2014-12-15 | Vpalamountain | High school | Decide number of tables/exhibitors | Psaternye | 2015-01-15 | 2014-12-18 | Coordination | 45-50 tables
003 | 2014-12-15 | Vpalamountain | None | Select a name for the event | Jbland | 2014-12-30 | 2014-12-18 | All | Volunteer Fluvanna!
004 | 2014-12-15 | Vpalamountain | Steering Committee | Complete form to use FCHS on 3/21/15 | Ccarr | 2015-01-15 |  | Coordination
005 | 2014-12-18 | Vpalamountain | All Committees | Send list of committee members to Steering Committee | Jbland, Jdown, Psaternye, Vpalamountain | 2014-12-18 | 2014-12-21
006 | 2014-12-18 | Vpalamountain | Library | Library volunteer day debriefing | Ehess | 2015-01-15
007 | 2014-12-18 | Vpalamountain | None | Set up collaboration site | Pdempsey | 2014-12-18 | 2014-12-18
008 | 2014-12-18 | Vpalamountain | All Committees | Develop budget | Vpalamountain | 2015-01-15
009 | 2014-12-18 | Vpalamountain | All Committees | Develop project plan | Vpalamountain | 2015-01-15
010 | 2014-12-18 | Vpalamountain | None | Establish attendance goal | Jbland | 2014-12-30 | 2014-12-18 |  | 175-200 people
011 | 2014-12-23 |  | Steering Committee | Costs related to culinary | Psaternye | 2015-01-15
012 | 2014-12-23 |  | Coordination | Costs related to security | Psaternye | 2015-01-15
013 | 2014-12-30 |  | Coordination | Floor plan of the high school | Ehess | 2015-01-15
014 | 2014-12-30 |  | Logistics | Tour of the school with custodians | Psaternye | 2015-01-15
015 | 2014-12-30 |  | Marketing | Deadline for Nonprofits to register. | Jbland | 2015-01-15 | 2014-12-30 |  | Deadline to register is 3/9/15.

## Committees
First Name | Last Name | Email | Committee
Stephanie | Davis | smokeycontracts@gmail.com | Coordination
John | Down | johndown9846@hotmail.com | Coordination | Chair
Eric | Hess | ehess@fluvannasheriff.com | Coordination
Delores | Hubert | dcirrusdj@yahoo.com | Coordination
Rick | Parkington | rparkington@innovationrelevance.com | Coordination
Valerie | Palamountain | vpalamountain@pvcc.edu | Executive | Chair
Mark | Dunning | cmdun047@gmail.com | Executive
Amy | Kirchner | ackirchner@gmail.com | Executive
Jennie | Shuklis | director@fspca.org | Executive
Bob | Dorsey | bobdorsey58@gmail.com | Executive
Paty | Saternye | pcsaternye@hotmail.com | Logistics | Chair
Leslie | Cloyd | samandleslie1@centurylink.net | Logistics
Faye | Dorsey | dorseyfaye@gmail.com | Logistics
Campbell | Kidd | cakidd@juno.com | Logistics
Claire | Lowande | clowande@fluvannacounty.org | Logistics
Brian | Miller | bjm8m@virginia.edu | Logistics
Tristana | Treadway | tristana@treadwaylaw.net | Logistics
Deborah | Wells | wellsd@charlottesville.org | Logistics
John | Wilkinson | atlibjw@gmail.com | Logistics
Jackie | Bland | misprint0949@gmail.com | Marketing | Chair
Kay | Carter | kc27507@gmail.com | Marketing
Pam | Dempsey | office@saintspeterpaul.org | Marketing
Susan | Lang | susanlang100@gmail.com | Marketing
Fred | Lang | profml2008@gmail.com | Marketing
Mary Jane | Whitney | mwhitney601@gmail.com | Marketing
Drew | Willson | pastor.drew.willson@gmail.com | Marketing

## Schedule
Description | Assigned To | Target Finish Date | Actual Finish Date | Notes
Complete Facilities Usage Form. | Steering | 2015-01-09 |  | Steering Committee needs to submit the form.
Submit cost items to Exec Committee. | All Committees | 2015-01-05
Develop event budget. | Executive | 2015-01-10
Approve event budget. | Steering | 2015-01-15
Secure space. | Steering | 2015-01-15
Tour facility. | Logistics | 2015-01-15
Get copy of the floor plan of the high school. | Coordination | 2015-01-09
Decide if culinary students should be involved. | Logistics | 2015-01-15 |  | No food due to cost, clean up and space to store it.
Decide the deadline for registration. | Marketing | 2015-01-15 | 2015-01-02 | Deadline is March 11.
Notify Committees of approved budget. | Executive | 2015-01-16
Develop flier. | Marketing | 2015-01-31
Develop Nonprofit registration form. | Marketing | 2015-01-31
Develop floor plan layout for the space. | Logistics | 2015-01-31
Develop registration process. | Marketing | 2015-01-31
Meet with Fluvanna Review for article. | Marketing | 2015-02-15
Send out nonprofit registration form. | Marketing | 2015-02-15
Identify security needs. | Logistics | 2015-02-15
Develop agenda for day of Event | Executive | 2015-02-15
Recruit volunteers for day of Event. | Logistics | 2015-03-01
Promote, promote, promote! | Marketing | 2015-03-20
Manage schedule and budget. | Executive | 2015-03-21
EVENT! | ALL | 2015-03-21

## Budget
Item | Number | Per Unit Cost | Cost | Notes
Marketing
Exhibitor flyer | 100 |  |  | County will print from print-ready files.
Attendee flyer | 5000 |  |  | Can the County make color copies?
Badges for FLDP Class |  |  | 0
Postage | 100 | 0.5 | 50
Banner 3'x5'
Signs/Posters |  |  |  | Can the County make color copies?
FLDP Giveaways | 200 | 3 | 600
Handouts/Map at Event |  |  |  | Can the County make color copies?
Logistics
Custodial |  |  | 240
Coordination
Executive
Total |  |  | 890

## Post Event Review
Goal | Plan | Stretch Goal | Actual | Outcome
No. of Nonprofits | 35 | 45
No. of Attendees | 175 | 200

## Days to Event
Description | Assigned To: | Days to Event | Notes
Complete Facility Usage Form. | Steering Committee | -180
Manage schedule and budget. | Executive Committee | -160
Draft preliminary budget | Exec Committee | -140
Decide if there is a fee for the Nonprofits. | Exec Committee | -120
Decide if there will be food at the event for Class. | Exec Committee | -120
Decide if there will be food at the event for Nonprofits. | Exec Committee | -120
Decide if there will be food at the event for the public. | Exec Committee | -120
Decide if there will be speakers. | Exec Committee | -120
Decide if A/V equipment is needed. | Exec Committee | -120
Develop email list of Nonprofits. | Marketing Committee | -120
Decide number of hours for the event. | Exec Committee | -120
Submit cost items to Exec Committee. | All Committees | -100
Develop event budget. | Exec Committee | -100
Confirm facility. | Steering Committee | -100
Develop flier. | Marketing Committee | -90
Develop nonprofit registration form. | Marketing Committee | -90
Develop registration process. | Marketing Committee | -90
Identify security needs. | Logistics Committee | -90
Approve event budget. | Steering Committee | -90
Tour facility. | Logistics Committee | -90
Decide the deadline for registration. | Marketing Committee | -90
Notify Committees of approved budget. | Executive Committee | -90
Design fliers and brochures. | Marketing Committee | -90
Develop floor plan layout for the space. | Logistics Committee | -75
Begin promotion | Marketing Committee | -75
Meet with Fluvanna Review for article. | Marketin g Committee | -75
Send out nonprofit registration form. | Marketing Committee | -75
Print fliers. | Marketing Committee | -75
Develop agenda for day of Event | Executive Committee | -60
Recruit volunteers for day of Event. | Logistics Committee | -60
Register nonprofits and assign tables. | Logistics Committee | -60
Develop team leaders for day of Event tasks. | Logistics Committee | -30
Assign volunteers | Logistics Committee | -15
Set up tables. | Logistics Committee | -1
EVENT! | ALL | 0

## Important Contacts
Name | Title | Phone | Email
Steve Nichols | County Administrator | 434-591-1910 | snichols@fluvannacounty.org
Rudy Garcia | FLDP Steering Committee | 850-776-9209 | rudy.garcia@hbwadvisory.com
Carol Tracy Carr | FLDP Steering Committee |  | caroltracycarr@me.com
Susan Beattie | FLDP Steering Committee | 434-242-2574 | goose@rakun.com
James Barlow | Principal, FCHS | 434-589-3666 | jbarlow@apps.fluco.org
Mr. Morris | FCHS